District Review Meeting

| S.No. | Actions to be taken till next Monthly Review Meeting |
| --- | --- |
| 1 | Accounts: PFMS (Public Financial Management System) - All districts to use PFMS and ensure its usage at block, cluster and school level. - Constitution of a local purchase committee as per the provisions of Samagra Shiksha Manual on Financial Management & Procurement (Rule 146 of GFR 2005 and GFR 2017) - Proper and timely utilization of funds by the blocks, clusters and schools. - Resolve the issues related to utilization of funds, in coordination with Accounts wing and concerned officials at various levels, if any. - Proper guidelines should be issued to blocks, clusters and schools regarding usage of funds under intimation to SPO. - Directions to ensure 100% fund utilization allocated under various heads. - DPOs to submit the list of blocks/ clusters/ schools slow in funds utilization, in the next meeting. |
| 2 | Online Monitoring- PMS Portal (Project Monitoring System) - All Districts to make provisional entry of the expenditure of previous month by 5th of every month so that GOI could be reported by 10th of the same month, in the Online Monitoring- PMS Portal using District User ID. - All Districts to make entry of CWSN in the same Online Monitoring- PMS Portal. - It is also mandatory to make entries pertaining to other interventions on the same. |
| 3 | Management Information System (MIS) - DPOs to go through the UDISE reports of 2018-19 data and look into the gaps if any in their respective districts. - All districts to develop their website (if not developed yet) as per the instruction of GOI. - DPOs were asked to hold regular meetings with all the school heads to ensure veracity of school level information being supplied through UDISE - DCF for effective implementation of all the Samagra Shiksha interventions. - Updating data on UDISE+, Online Monitoring- PMS, Shagunotsav, DIETs websites, Shagun Portal etc.This influences the indicators for PGI which determines the ranking of a State at the national-level |
| 4 | Civil Works - All districts to expedite all civil works and monitor the progress on weekly bases in coordination with state coordinators, JEs, construction agencies, line departments, school heads, SMCs etc. and to make best efforts for sites availability so that work could be started. - JEs to visit the concerned Division offices regularly to update the progress of works. - All the DPOs must start the work of each component as the money has already been released to all districts under capital (General Head) though PFMS dated 20th Nov., 2019. The progress of each of these works will be reviewed in the next meeting. - Utilization certificates of all previous civil works executed by SMCs may be collected at the district level for which funds were already provided/ released to the districts. - Time line decided for the action and completion of each of the works may be strictly adhered to. - All DPOs to submit progress report in next State Review Meeting. - Civil works (RMSA & Elementary) and Distribution of funds for Civil Works (Elementary) under Samagra Shiksha (2019-20) are listed as Annexure-A. - Solve the issues identified from visit reports, available at Visits in Primary Schools/ Elementary Schools/ Higher Grades dashboards and check the Action Point Tracker. |
| 5 | Pre-Primary Education - All Districts to utilize released funds. The funds being released for each pre-primary school are as follows: - Teaching Learning Material: Rs. 10,000/- - Play material: Rs. 10,000/- - School Readiness (BaLA): Rs. 40,000/- - Detailed guidelines in this regard will be shared separately. - DPOs to ensure / check that these funds are utilized in a right and transparent manner in pre-primary schools. |
| 6 | SMC - All Districts to organize all block level trainings of SMCs (Elementary and Secondary both) by 15th December, 2019. - All Districts to complete the second phase of Shiksha Samwad in all the schools by 30th November, 2019 as per directions already issued by this office. - In addition, UCs of three days training of teachers on National Action Plan on Drug Demand Reduction may be submitted to SPO (SS) by 25-11-2019. - At least 2 best practices on community participation may also be shared in the next review meeting. - Best SMCs may also be selected at Cluster, Block and District level to honor them with appreciation and incentives. - Solve the issues identified from visit reports, available at Visits in Primary Schools/ Elementary Schools/ Higher Grades dashboards and check the Action Point Tracker. |
| 7 | Review and Monitoring - All DPOs to ensure academic support by mentoring, monitoring and review meetings with Special focus on quality of education. - All DPOs to ensure usage of Inspection Dashboard available at www.edumis.hp.gov.in (Review and Monitoring) to know about; - Monthly school visit data (available at Monthly Visit Compliance dashboard) - List of schools already visited (available at Details of Schools Visited dashboard) - Detail of issues identified from visit reports submitted by various officials, available at Visits in Elementary Schools dashboard and Visits in Higher Grades dashboard which must be discussed in District and Block Review Meetings, held in coordination with DDHE, DDEE, BPOs, BEEOs and BRCCs to fix the accountability and resolve the issues. - Detail of issues identified from visit reports submitted by CHTs, available at Visits in Primary Schools/ Elementary Schools/ Higher Grades dashboard which must be discussed in Block and Cluster Review Meetings, held in coordination with BPOs, BEEOs, BRCCs and CRCCs to fix the accountability and resolve the issues. - All the DDEE to initiate action against BEEOs and CRCCs who do not visit targeted schools, under intimation to Director Elementary Education and SPD (SS). - All the DPOs to initiate action against BRCCs (Primary and Upper Primary) who do not visit targeted schools, under intimation to State Project Director (SS). - To update Action Point Tracker and submit District Review Meeting Form by District R&M Coordinator. - DPOs to direct all the BRCCs & CRCCs to conduct Block and Cluster level meetings and observe above mentioned dashboards, Action Point Tracker and submit Block/ Cluster Review Meeting Form. - All the R&M coordinators to prepare Micro Plan of the District in coordination with DPOs, DDHE, DDEE, BPOs, BEEOs, BRCCs and CRCCs to visit each school at least twice in the academic year and to prepare strategy to provide academic support based on findings of Monitoring Reports. - Meeting to be conducted before 10th of every month. The details of the meeting agenda and the meeting minutes form are available on SSA website. |
| 8 | Shagunotsav - All DPOs to ensure effective conduct of Shagunotsav. This is a Census Based Audit of Government and Government Aided schools to ensure authenticity of data provided under various methods e.g., UDISE+, PGI, Samagra Shiksha, Mid-Day Meal and Disaster Management etc. - This survey will be started as per guidelines of MHRD to assess the status of all government schools on various key indicators. - All DDHE/ DDEE/ DPOs to share Questionnaire of Shagunotsav with BPOs/ BEEOs/ BRCCs/ CRCCs and to the Schools and support their schools accordingly. |
| 9 | Assessment and Evaluation - Distribution of question papers for SA-II in winter closing schools well in time. - The list of A graders and 100% attendance students of schools should be displayed on bulletin board of every school at the time of declaration of result i.e. 31st Dec., 2019 (winter closing schools) and 31st March, 2020 (summer closing schools). - Schools must be visited during SA-II assessment & evaluation of answer sheets using Shiksha Saathi App. - Ensure delivery and usage of LO question banks at the school level to evaluate the students for improvement of their learning outcomes - Cluster heads to have special emphasis on learning outcome-based teaching and evaluation - Link for question banks Primary (1st - 5th) –http://bit.ly/primaryqb - Link for question banks Upper primary (6th - 8th) –http://bit.ly/upperprimaryqb - Usage of Assessment Dashboard to ensure that all schools identify their weak learning outcomes from the HP Samarth Assessment Dashboard (hpsamarth.com) and focus on them for revision.Ensure copy of assessment dashboard is pasted in the premises. - Feedback/challenges on the assessment dashboard can be shared here - http://bit.do/assessmentdashboardfeedback - Link of the training module explaining how to use the assessment dashboard:http://bit.do/assessment-dashboard-training-module - Solve the issues identified from visit reports, available at Visits in Primary Schools/ Elementary Schools/ Higher Grades dashboards and check the Action Point Tracker (Shiksha Saathi App). |
| 10 | Quality Initiatives - All concerned to work in coordination for proper Implementation of NISHTHA at all levels. - Refresher Training for Teachers: Motivate the teachers to complete the courses assigned for a particular month on The Teacher App under the Continuous Learning Program. - Seekhne Ka Pitaara: Ensure usage of supplementary material. Please watch the training video during the meeting to understand the details of the program: http://bit.do/seekhne-ka-pitaara-training-module - Exposure visits to Science Center at DIET Bilaspur. - Create awareness among teachers to prepare students for NAS-2020 and PISA. - Facilitate usage of ZIIE App as and when required by teachers. - Solve issues identified from visit reports, available at Visits in Primary Schools/ Elementary Schools/ Higher Grades dashboards and check the Action Point Tracker (Shiksha Saathi App). |
| 11 | KGBVs - Proper and timely utilization of budget under this intervention - Ensure implementation of activities under the interventions as directed by the State Project Office and update the status |
| 12 | Implementation of School Leadership Development Programme - Districts were directed to maintain the data base of the training of school heads on School Leadership Development on the format shared. - At least one case study of each school (Pry, Middle, High & Senior Secondary) and one video documentary of 2-3 minutes may be prepared and shared with the SPO (SS) and NCSL website of NIEPA. - For the year 2019-20, 360 school heads have to be trained under SLDP (30 school heads in each district). |
| 13 | OoSC - Proper and timely utilization of budget under this intervention - Ensure implementation of activities under the interventions as directed by the State Project Office and update the status - To solve issues identified from visit reports, available at Visits in Primary Schools/ Elementary Schools/ Higher Grades dashboards and to update the Action Point Tracker. |
| 14 | Inclusive Education for Differently abled at Secondary stage (IEDSS) - All DPOs to submit Budget Plan under IEDSS (IX-XII) - 2020-21 (As per UDISE+ 2019) @ 3500 per CWSN. Sample table shared with DPOs. - All Districts were asked to enter CWSN (Boys and Girls) in the District PMIS (Samagra Shiksha Portal). - Districts to start the process to purchase Braille Books Sets for Visually Impaired CWSN (IX-XII) for next session. As per UDISE+. - All Districts to submit at least 2 best practices of IEDSS (Report with photographs) in the next review meeting. - All DPOs to direct Special Educators to make efforts to improve learning outcomes of CWSN as per NCERTguidelines. - To solve issues identified from visit reports, available at Visits in Primary Schools/ Elementary Schools/ Higher Grades dashboards and to update the Action Point Tracker. - Meeting of IEDSS coordinators will be held in last week of December, 2019 to review the progress. - Coordinators to submit progress report as per activities mentioned for FY 2019-20 and best practices report/ documentaries/ videos etc. |
| 15 | ICT - DPOs to ensure the best possible use of ICT infrastructure wherever this facility / learning resource has been made available in schools. - ICT Phase II schools are required to sync both their KYANs to the server using internet. All schools must ensure that the usage for previous month is synced by 5th of every month. The following tutorial video explains the steps to be followed to sync KYAN usage data: http://bit.do/kyansync - To solve issues identified from visit reports, available at Visits in Primary Schools/ Elementary Schools/ Higher Grades dashboards and check the Action Point Tracker. |
| 16 | Quality interventions in Secondary and Senior Classes - Usage of Swayamsidham portal for self-study content, assessment sheets and question banks for science stream of 11th and 12th - To ensure monthly subject wise class tests - Organizing Quiz Competitions at secondary level - To solve issues identified from visit reports, available at Visits in Higher Grades dashboards and check the Action Point Tracker. |
| 17 | Implementation of Section 12 of RTE Act 2009 - Ensure awareness of RTE section 12 and implementation of activities under the interventions as directed by the State Project Office and update the status. - To solve issues identified from visit reports, available at Visits in Primary Schools/ Elementary Schools/ Higher Grades dashboards and check the Action Point Tracker. |
| 18 | DIETS - DPOs will ensure that the teaching practice in schools is conducted in a proper manner by adopting the process laid down in the workbook designed by the NIOS for the said purpose. - Work for State Youth Meet of all the DIETs in district Una may also be planned and organized in the month of March/April, 2020. |

Annexure-A

List of 85 schools for execution under strengthening for the FY 2016-17 under RMSA

| S. | District | School Code | School | Science lab | Computer Room | Art Craft & culture Room | Library | A C R | Amount approved for construction (in Lacs) | Status of works |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | KANGRA | 2021200902 | GSSS BAROH | 0 | 0 | 1 | 1 | 0 | 22.00 |  |
| 2 | KANGRA | 2021507302 | GSSS DADH | 1 | 1 | 0 | 0 | 0 | 18.00 |  |
| 3 | KANGRA | 2021908202 | GSSS SALETI | 0 | 0 | 1 | 1 | 0 | 22.00 |  |
| 4 | KULLU | 2040402006 | GSSS CHANON | 1 | 0 | 1 | 1 | 1 | 40.53 | Tender canceled due to single bidder received and tender again recalled. Work targeted 2018-19 |
| 5 | KULLU | 2040501704 | GSSS KHUN | 1 | 0 | 1 | 1 | 0 | 31.00 | Working estimate under process in Division office. |
| 6 | MANDI | 2051000101 | GSSS KHUNACHI | 1 | 1 | 1 | 1 | 0 | 40.00 | The working drawing stands submitted to Director Higher Education Shimla for its approval vide Senior Architect Mandi letter No. 977-81 dated 07-02-2018. |
| 7 | MANDI | 2051000901 | GSSS SARACHI | 1 | 1 | 1 | 1 | 2 | 59.06 | Tender opened on 12-02-2018 and under process of award in divisional office. |
| 8 | MANDI | 2051007903 | G.H.S SERIBATWARA | 1 | 1 | 1 | 1 | 0 | 40.00 | Tender opened on 20-03-2018 and under process of award in divisional office. |
| 9 | MANDI | 2051106603 | GHS KUTGARH | 1 | 0 | 1 | 1 | 0 | 31.00 | Site not handed over till date. |
| 10 | MANDI | 2051108102 | GSSS BIHUN | 0 | 0 | 1 | 1 | 0 | 22.00 | Site not handed over by the client department. |
| 11 | MANDI | 2051311502 | GHS SAGNEHAR | 1 | 0 | 1 | 1 | 0 | 31.00 | Land not available.Tender yet to be called.Old building yet to be dismentalled.Not started. |
| 12 | MANDI | 2051709502 | GHS PINGLA | 1 | 1 | 1 | 1 | 0 | 40.00 | Working estimate under preparation in divisional office. Tender is being invited. |
| 13 | UNA | 2070207202 | GHS AJOULI | 1 | 0 | 1 | 1 | 0 | 31.00 | Working estimate under preparation in divisional office. Tender is being invited. |
| 14 | UNA | 2070604002 | GSSS PIPLOO | 1 | 0 | 1 | 1 | 0 | 31.00 | Working estimate under preparation in divisional office. Tender is being invited. |
| 15 | BILASPUR | 2080219402 | GSSS BADDU (DADHOG) | 1 | 1 | 1 | 1 | 0 | 40.00 | Working estimate under preparation in divisional office. Tender is being invited. |
| 16 | BILASPUR | 2080302603 | GSSS BHAROLI KALAN | 0 | 0 | 1 | 1 | 0 | 22.00 | Working estimate under preparation in divisional office. Tender is being invited. |
| 17 | BILASPUR | 2080414702 | GHS SOHAL | 1 | 1 | 1 | 1 | 0 | 40.00 | Working estimate under preparation in divisional office. Tender is being invited. |
| 18 | SOLAN | 2090506101 | GSSS BANI MATERNI | 1 | 0 | 1 | 1 | 0 | 31.00 | Working estimate under preparation in divisional office. Tender is being invited. |
| 19 | SIRMAUR | 2100607702 | GHS KOTLA BANGI | 1 | 1 | 1 | 1 | 1 | 49.53 | Working estimate under preparation in divisional office. Tender is being invited. |
| 20 | SHIMLA | 2110305802 | GSSS DEHA(BALSON) | 0 | 0 | 0 | 0 | 1 | 9.53 | Working estimate under preparation in divisional office. Tender is being invited. |
| 21 | SHIMLA | 2110901402 | GSSS GUMMA | 0 | 0 | 1 | 1 | 0 | 22.00 | Working estimate under preparation in divisional office. Tender is being invited. |
| 22 | SHIMLA | 2111402302 | GSSS BHALOON | 1 | 0 | 1 | 1 | 1 | 40.53 | Working estimate under preparation in divisional office. Tender is being invited. |
| 23 | SHIMLA | 2111503902 | GSSS KOHBAG | 0 | 0 | 1 | 1 | 1 | 31.53 | Work not Started (A/A&E/S awaited) |
| 24 | SHIMLA | 2111604702 | GSSS THAILA (SHAHEED N.K) | 0 | 0 | 1 | 1 | 0 | 22.00 | Tenders being called |
| 25 | SHIMLA | 2111606802 | GSSS CHANWAG | 1 | 1 | 1 | 1 | 0 | 40.00 | Tender being called. |
| 26 | KINNAUR | 2120200901 | G.H.S. BRUA | 1 | 0 | 1 | 1 | 0 | 31.00 | Working estimate under process in Division office. |
|  |  |  |  | 18 | 9 | 24 | 24 | 7 | 837.71 |  |

Civil Works under Elementary Education (2018-19)

| Sl. No | Districts | Name of Works |  | Total Phy. & Fin. | Completion/ Utilization as on 31.10.2019 |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Phy | Remarks /Status as on 31.08.2019 | Complete | In progress | Not started |  |
| 1 | Bilaspur | Drinking Water | 8 | 4.00 | 3 | 0 | 5 | Matter of land dispute may be decided up to 30.12.2019 |
|  |  | Ramps and handrail | 54 | 8.10 | 37 | 17 | 0 | The district should ensure the completion of 17 ramps with handrails by 31.12.2019 |
| 2 | Chamba | Additional classroom | 13 | 80.50 | 6 | 3 | 4 | Land dispute is settled. District may start the work of 3 Rooms immediately. |
|  |  | Ramps and handrail | 119 | 17.50 | 84 | 22 | 13 | In progress works of Pangi Block may be completed immediately. |
| 3 | Kangra | Major Repair | 19 | 41.04 | 16 | 3 | 0 | May be completed by 31.12.2019 |
|  |  | Boundary wall | 2000 | 42.00 | 1400 | 190 | 410 | May be started the work immediately |
|  |  | Argumentation of BRCC | 11 | 55.00 | 3 | 8 | 0 | The district should ensure the completion BRCs by 31.12.2019 |
|  |  | Additional classroom | 9 | 58.50 | 1 | 6 | 2 | Completion of 6 classrooms may be ensured by 31.12.2019 |
|  |  |  |  |  |  |  |  | Two class rooms are not started till date due to SMC disputes. District may resolve the disputes up to dec, 2019, |
| 4 | Kullu | Additional classroom | 6 | 4.52 | 0 | 3 | 3 | District may start the work immediately |
| 5 | Lahaul-Spiti | New School building ( Upper Primary) | 2 | 44.00 | 1 | 1 | 0 | May be completed by 31.12.2019 |
| 6 | Mandi | Additional classroom | 3 | 19.50 | 0 | 3 | 0 | In progress classrooms may be completed by 30.11.2019 and I classroom completed within three months. |
|  |  | Girls Toilets | 61 | 45.75 | 35 | 25 | 1 | May be completed by 31.12.2019 |
|  |  | Major Repair | 5 | 5.61 | 3 | 2 | 0 |  |
| 7 | Shimla | Boys & girls Toilets | 1 | 0.75 | 0 | 0 | 1 | Land transfer case may be taken up on priority up to 31.12.2019 district administration. |
|  |  | Major Repair | 17 | 27.14 | 13 | 4 | 0 | The district should ensure the completion of 4 ( GPS Satal, GPS Jugger, GPS Bhootkanda, GMS Kotighat )in progress of repair works by 31.12.2019 |
|  |  | Electrification | 107 | 22.79 | 63 | 17 | 27 | May be completed by 31.12.2019 |
|  |  |  |  |  |  |  |  | Cases be taken up on priority in consultation with HIMURJA and district administration. |
|  |  | Augumentation of BRCC | 3 | 3.75 | 1 | 2 | 0 | May be completed by 31.12.2019 |
|  |  | Additional classroom | 1 | 6.50 | 0 | 1 | 0 | May be completed by 31.12.2019 |
| 8 | Sirmour | Boys Toilets | 13 | 5.15 | 9 | 0 | 4 | Land dispute cases be taken up on priority in consultation with district administration and start the work. |
|  |  | Girls Toilets | 12 | 4.75 | 8 | 0 | 4 |  |
| 9 | Solan | Additional classrooms | 4 | 26.00 | 0 | 2 | 2 | May be completed by 31.12.2019 |
|  |  | Building Less / Dilapidated Building | 1 | 25.00 | 0 | 1 | 0 | May be completed by 31.12.2019 |
| 10 | Una | New School building ( Upper Primary) | 4 | 73.00 | 2 | 2 | 0 | May be completed by 31.12.2019 |

Distribution of funds for Civil Works (Elementary) under Samagra Shiksha (2019-20)

| Sl. No | Districts | Name of Works | Spillover |  | Total Amount (Rs. in Lakh) |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Physical | Financial (Rs. in Lakh) |  |
| 1 | Bilaspur | Boundary Walls | 4266 | 48.58 |  |
|  |  | Sub total | 4266 | 48.58 | 48.58 |
| 2 | Chamba | Additional Classrooms | 1 | 6.5 |  |
|  |  | Boundary Walls | 576 | 7.55 |  |
|  |  | Ramps and Handrails | 13 | 1.6 |  |
|  |  | Sub total | 590 | 15.65 | 15.65 |
| 3 | Hamirpur | Ramps and Handrails | 22 | 3.3 |  |
|  |  | Sub total | 22 | 3.3 | 3.3 |
| 4 | Kangra | Boundary Walls | 14091 | 85.78 |  |
|  |  | Ramps and Handrails | 173 | 25.95 |  |
|  |  | Sub total | 14264 | 111.73 | 111.73 |
| 5 | Kinnaur | Ramps and Handrails | 12 | 1.8 |  |
|  |  | Boundary Walls | 932 | 17.59 |  |
|  |  | Sub total | 944 | 19.39 | 19.39 |
| 6 | Kullu | New Up-Primary School building (Up Gradation of Pry. to Up-pry) | 1 | 30 |  |
|  |  | Additional Classrooms | 3 | 7.71 |  |
|  |  | Boundary Walls | 0 | 95.38 |  |
|  |  | Ramps and Handrails | 97 | 14.55 |  |
|  |  | Sub total | 101 | 147.64 | 147.64 |
| 7 | Lahaul-Spiti | Boundary Walls | 3 | 3.64 |  |
|  |  | Ramps and Handrails | 218 | 32.7 |  |
|  |  | Sub total | 221 | 36.34 | 36.34 |
| 8 | Mandi | Boundary Walls | 60834 | 790.84 |  |
|  |  | Ramps and Handrails | 550 | 82.5 |  |
|  |  | Sub total | 61384 | 873.34 | 873.34 |
| 9 | Shimla | Additional Classrooms | 20 | 20.7 |  |
|  |  | Boundary Walls | 16549 | 176.64 |  |
|  |  | Ramps and Handrails | 66 | 9.9 |  |
|  |  | Sub total | 16635 | 207.24 | 207.24 |
| 10 | Sirmour | New Up-Primary School building (Up Gradation of Pry. to Up-pry) | 1 | 30 |  |
|  |  | Ramps and Handrails | 180 | 27 |  |
|  |  | Sub total | 181 | 57 | 57 |
| 11 | Solan | New Up-Primary School building (Up Gradation of Pry. to Up-pry) | 2 | 60 |  |
|  |  | Building Less Schools / Dilapidated Building | 1 | 18.75 |  |
|  |  | Additional Classrooms | 3 | 7 |  |
|  |  | Boundary Walls | 6061 | 46.05 |  |
|  |  | Ramps and Handrails | 102 | 15.15 |  |
|  |  | Sub total | 6169 | 146.95 | 146.95 |
| 12 | Una | Boundary Walls | 1400 | 18.2 |  |
|  |  | Ramps and Handrails | 112 | 16.8 |  |
|  |  | Sub total | 1512 | 35.00 | 35 |
|  |  |  |  | Total | 1702.16 |